## Screen05
Group | Process | Subprocess | PIC | Start | End | MH | Status
Frontend | Initial Display | 1. Retrieve/GET data from backend using axios for the Company List(Company DB), Team List(Team DB), Anken Info Area(Anken Info DB), Quotation Display(Anken DB) and Quotation Input Area(Quotation DB) | Tine
|  | 2. Show the list of company names under the company selection box VTable. | Alvi
|  | 3. Show the list of team names under the team selection box VTable. | Alvi
|  | 4. Show the Anken Info under the Anken Info VTable. (read only) | Tine | 2024-08-09 | 2024-08-09 | 5
|  | 5. Show the Quotation Display values (read only) | Joeff | 2024-08-09 | 2024-08-09 | 5 | DONE
|  | 6. Show only the lines(rows) based on the existing Quotation inputs that was previously registered. | Alvi
| Update Button | 1. Update 2 DB with the latest info of the Quotation Input Area (Quotation DB) and Quotation Display(Anken DB) | Joeff
|  | 2. Perform re-computation if it has not been pressed yet. | Joeff
|  | 3. Investigate how to determine which rows have been edited before update to DB | Joeff
|  | 4. Create/POST a record to the Change History DB based on the updated values. | Joeff
| Filter Button | 1. Narrow the Quotation Input display area based on the selected company and team. It will look into the PIC Group column. | Joeff
* When both company and team are selected, only narrow by team.
| Reference Output Button | 1. Output the Quotation Request and other uploaded files related to the ANK Devt. Request No. | Mias
|  | 2. If no materials present, output "Reference Material not found" | Mias
| Re-Calculation button | 1. Redisplay based on the Quotation Input (Please refer to formula) | Mias
| UI | Fix display with actual strings and dimensions for components.
Group | Process | Subprocess | PIC |  |  | MH | Status
Backend | Initial Display | 1. Create endpoint to GET data of Company List(Company DB) | Elwin
|  | 2. Create endpoint to GET data of Team List(Team DB) | Elwin
|  | 3. Create endpoint to GET data of Anken Info Area(Anken Info DB) | Elwin
|  | 4. Create endpoint to GET data of Quotation Display(Anken DB) | Angie | 2024-08-09 | 2024-08-09 | 2 | DONE
|  | 5. Create endpoint to GET data of Quotation Input Area(Quotation DB) | Angie | 2024-08-09 | 2024-08-09 | 3 | DONE
| Update Button | 1. Create endpoint to POST data from values in the Quotation Display Area to the Anken DB. Use the "ANK DEVT REL. NO " when creating the record. | Elwin
|  | 2. Create endpoint to POST data from values in the Quotation Input Area to the Quotation DB. Use the "ANK DEVT REL. NO " when creating the record. | Angie | 2024-08-12
| Reference Output Button | 1. Create GET endpoint to output the uploaded excel file related to this Anken Number | Angie